## Sheet1
|  | Description of Risk | Probability (1-10) | Impact (1-10) | Priority (probability * impact) | Triggers (if not obvious) | Response Plan
Technical: | Gripper | servo breaks without prompting | 2 | 5 | 10 |  | If servo is from china replace with one of the spares and order another. If servo is from UK, replace with spare and begin RMA process
|  | gripper self-destructs breaking servo | 3 | 5 | 15 |  | Replace servo with spare and order another spare
|  | gripper self-destructs breaking plastics | 3 | 2 | 6 |  | Re-print (one day lost)
kinect:
|  | Power supply voltage issues | 2 | 7 | 14 | Power supply moves more than 0.5v out of specification | Monitor closely for the first few days
|  | Runs too slowly on second PC | 4 | 3 | 12 | Major issues occur | Optimise hectorSLAM
|  | Issues translating kinect pixel numbers to coordinate referenced to any robot frame | 3 | 8 | 24 |  | Seek advice on TF from lecturers, if that doesn't work then group meeting (and both work on solution)
Gripper vision:
|  | fractal QR codes don't work | 5 | 8 | 40 |  | Solution explained in main execution plan
|  | camera too close, fractal QR code doesn't work | 6 | 8 | 48 |  | " " " " " " " " " " " " "
|  | gripper/kinect vision uses up too many computational resources causing issues with kinematic calculations resulting in: |  |  |  |  | Optimise hectorSLAM to reduce computational requirements
|  | Non-smooth trajectories | 5 | 2 | 10 |  | Minor issue
|  | Jumping | 4 | 3 | 12 |  | Medium issue, investivate
|  | collisions with other objects | 3 | 6 | 18 |  | Major issue, re-evaulate computational requirements
|  | Collisions with self | 3 | 6 | 18 |  | " " " " " " " " " " " "
|  | gripper can't deform to shape of object properly, can't pick object up | 3 | 6 | 18 | Object frequently drops from gripper | Attach 'bag' to gripper, if tht fails discuss redesign
localisation:
Robot crashes into walls/things resulting in:
|  | breaks nothing | 8 | 1 | 8 |  | Be more careful
|  | breaks arm plastics | 3 | 6 | 18 |  | Re-print (two days lost)
|  | breaks arm servo | 3 | 9 |  |  | Major issue, redesign testing approach, look for replacement whilst initiating RMA to korea
|  | breaks encoder | 3 | 6 | 18 |  | Fix encoder (two days lost)
|  | robot can't get close enough to object (more than once or twice) | 3 | 7 | 21 |  | Tune navigation systems, if fails then team meeting
object mapping:
|  | Robot can't see far away objects (1.5m+) | 3 | 7 | 21 |  | Should be addressed in development phase 1
|  | robot falsly identifies objects | 2 | 7 | 14 |  | Both team members quickly construct a filter where a number of successful matches have to happen in sequence in order to trigger 'object found'
arm mounting:
|  | arm falls off leading to damage of arm | 3 | 7 | 21 |  | Major issue, reevaluate testing
|  | arm overbalances base | 2 | 9 | 18 |  | Major issue, should never happen. Back of envelope calculations should be done to analyse potential moments between arm and base
systems integration:
|  | must and can't stop/pause SLAM without remapping room | 4 | 9 | 36 |  | Group meeting, consider archetecture re-design
| object falls out of gripper often |  | 3 | 7 | 21
|  | risk: invacare remote finally dies | 3 | 7 | 21 |  | reserve budget to buy new controller
Planning: |  | Fiinished subsystems performance criteria not strict enough to allow for autonomous interaction between subsystems | 3 | 7 | 21 | Unacceptable performance of interaction between systems | Carefully re-evaluate performance criteria of subsystems, potentially suggest alternative subsystems
Human:
|  | lab is frequently full of people during testing/development, scrambles SLAM | 4 | 8 | 32 | More than two days spent at low productivity due to people walking nearby
|  | Getting caught in the details of a subsystem, spending too long trying to fix unexpected issues in a subsystem | 7 | 7 | 49 | Subsystem developent time exceeded | Group meeting, analyse alternative subsystems/different ways of achieving the same thing
risk: Tom/Dan falls ill for:
|  | 1 week | 2 | 7 | 14 |  | Must catch up with lost work, consider extenuating circumstances
|  | 2-4 weeks | 2 | 8 | 16 |  | Significant issue, discuss catching up, probably reduce project scope, consider extenuating circumstances
|  | 4-8 weeks | 1 | 9 | 9 |  | Major issue, reduce scope and file for extenuating circumstances
|  | 8 weeks + | 1 | 10 | 10 |  | Major issue, drastically reduce scope and file for extenuating circumstances
|  | CAD could take longer than planned | 3 | 3 | 9 | CAD development time exceeded | Remaining workload redistributed between us
human/time: |  | Systems integration takes longer than planned (applicable for interaction between every system&subsystem) | 7 | 7 | 49 | Systems integration time exceeded (or looks like it will be) | Reduce scope of project, re-evaluate priority list, divert attention from lower priority tasks, look for potential off-the shelf solutions (unlikely to find any)
|  | Risk: we lose access to the arm from Martin | 1 | 10 | 10 |  | Unlikey and catastrophic, total re-design of project goals
Resources: |  | Printers unavailable / break | 2 | 2 | 4 |  | Unlikely, we have two personal printers and at least three available in University
Logistics: |  | long lead times | 8 | 4 | 32 |  | Plan accordingly, all long-lead items to be specified within the first week of February
|  | can't return servos if faulty / break | 6 | 6 | 36 |  | Order more servos if our surplus falls below two
|  | can't get PCB made | 1 | 8 | 8 |  | Point to point wiring
Other: |  | We lose the laptop | 2 | 9 | 18 |  | Insure laptop, major issue